## Slide 1: ASN (RNET 3B2) Implementation Package
Saufi Bukhari
Systems Analyst
June 20, 2012

## Slide 2: Inbound Freight Visibility
Key Challenge
Improve visibility of inbound freight spends and support continued capability development to optimize the inbound freight supply chain.
Current State Key Gap
Foundational data to get specific PO line shipments linked to freight invoice information.

## Slide 3: Project’s Benefits
Supplier Benefits
B2B: Direct connection to Intel, no translation errors
Intel Benefits
B2B/Web: Direct connection and linkage to other Intel supply chain systems, minimized data quality (DQ) issues
Web: Auto-population of key information, minimized manual data entry
Overall: Reduction of status updates to Intel. Tracking enabled via BOL/HAWB identification
Overall: Quicker processing of shipment information, improved payment possibilities
Note: Many Intel suppliers confirm usefulness of ASN transaction for improving supply chain success
Overall: Advanced notification of shipment to prepare lane/receiving for shipments..reduced cycle time
Overall: Enables systematic tracking vs. time consuming phone conversation or tracking spreadsheets
Overall: Enables proactive identification of shipping issues

## Slide 4: Supplier Roles and Responsibilities
Business Representative
  Arrange resource(s) from supplier side
  Make business decision
IT (Systems Analyst)
  Responsible to configure test environment
  Execute B2B testing with Intel to test the functionality of new implementation/changes
  Troubleshoot and propose solutions during testing phases
Developer / Programmer
  Perform development based on Intel specifications
User
  Process the PO (from Intel) and create ASN to be triggered to Intel

## Slide 5: ASN Scope
Direct shipments from supplier to Intel
Basic flow:
  Supplier sends the physical shipment and triggers 3B2 to Intel to notify about the shipment
Note:
  ASN needs to be sent within +/- 4 Hours from actual shipment from supplier’s Dock
  Only one PO# to reference per ASN
  ShippingContainer structure can loop multiple times, ShippingContainerItem can loop multiple times within the same ShippingContainer.
  Within one ShippingContainerItem, there can only be one PO#, one PO Line#, and one Lot# referenced
Supplier
Intel
3B2
3B2 Advanced Shipment Notification
Physical shipment

## Slide 6: Business Requirements
PO # and PO Line #
Part Number
Vendor ID
Tracking Information – HAWB / MAWB / BOL
Ship Date and Arrival Date
Weight
Shipped Quantity
Packing Slip # or Shipment #
Note: Supplier can request detailed information from B2B systems analyst when ready to start ASN project
  Scope
  This is project only covers Intel Managed Freight
  Ex. Incoterms- FCA, FOB and EX-Works

## Slide 7: New 3B2 Implementation
For existing supplier with other RNET PIPs (without 3B2 ready):
  Approximately 8 weeks to complete (from development until UAT)
  Initial Business Engagement (2 weeks)
  Development (2 weeks)
  L1 Testing – connectivity (1 week)
  L2 Testing – syntax checking (1-2 weeks)
  L3 Testing – system testing (2-4 weeks)
  UAT – user acceptance testing (1-2 weeks)

## Slide 8: Phase Details
Initial Business Engagement: 2 weeks
  Hold Pre-Kickoff meeting with Commodity Team/Supplier/Data Quality
  Verify Business model and Supplier Infrastructure
  Hold Kick-Off meeting with Commodity Team/Supplier
    Gain agreement/buy-in from team on Intel proposal and/or supplier plan
    Communicate changes, training , schedule etc.
  Owner: Commodity manager pulls team together
Development: 2 weeks
  Engage with supplier to review the requirement and mapping, propose solution, and commit timeline
  Gather information to be setup (especially for new implementation)
  Prepare test data
  Owner: Intel technical team and supplier technical team
L1 testing: 1 week
  Configure test environment
    Firewall configuration (if required)
    Middleware configuration (if required)
    Back-end system configuration (if required)
  Connectivity test (firewall to firewall)
  Owner: Intel technical team and supplier technical team

## Slide 9: Phase Details
L2 Testing: 1-2 weeks
  Syntax check (middleware to middleware)
  Ensure the 3B2 format satisfies Intel’s mapping and specifications
  Owner: Intel technical team and supplier technical team
L3 Testing: 2-4 weeks
  System test (end to end)
  Ensure the 3B2 processed successfully by back-end system (SAP)
  Buyer to create PO’s for CONS for testing (Biz)
  Owner: Intel technical team and supplier technical team
User Acceptance Testing (UAT): 1-2 weeks
  End to end test with end user involvement
  Ensure the 3B2 processed successfully with end user involvement
  Owner: Commodity manager makes GO decision
Go-live
  After completing the test
  Deploy new changes or implementation in production environment
  Business need to drive the deployment
  Stabilization period (1-2 weeks) will take place to ensure the B2B transactions are working fine
  Owner: Intel technical team and supplier technical team

## Slide 10: Process Flow
Commodity
Manager
Intel IT
Supplier
Inbound
Transportation
Network Team
Initial Business Engagement
Go Live
User Acceptance
Development & Testing
Escalation and Ongoing Monitoring

## Slide 12: 声明：
所有的版权属于原有公司，文件均来自公开渠道
此文件仅供学习使用，任何人不得进行以此为商业目的的行为
如有疑问，请立即删除
https://www.chuanke.com
https://study.163.com
学习世界五百强和咨询公司PPT课程请访问如下网站搜索：“司马懿”
https://www.zhiu.com
百度传课：司马懿PPT学校
网易学堂：司马懿PPT学校
知乎： 司马懿PPT学校